TAX JUSTICE CAMPAIGN IN KENYA

**ONE YEAR ACTION PLAN (2014)**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ACTIVITY** | **TASKS** | **ACTION BY** | **TIMELINE** | **TARGET GROUP** | **ACHIEVEMENTS** |
| **Reporting back on the Abuja tax justice meeting resolutions.** | **Writing a report and making presentation or direct meetings to PSI sub- regional secretary.**  **-Reporting to the GSs.** | **Matilda ,Dickens Atela and Sani Baba** | **20TH TO 30TH JAN 2014** | * **Union General Secretaries.** * **PSI sub-regional office.** | * **The sub-regional PSI secretary to inform Union affiliate heads ( GSs) on the tax justice activity .** * **incorporation of tax justice in the Union training programs** |
| **Capacity building /training** | **-Training of TOTs (preferably Education officers) from all the PSI affiliate unions.** | **Dickens Atela & Matilda with help/ consultation from tax justice Africa.** | **March 2014** | **Education officers/ Trainers** | * **2 meetings .** * **40 Trainers trained.** |
| **Preparation of advocacy materials** | **Reading and analyzing of tax justice training materials , tax justice toolkit (PUPs materials), PSI tools and COTU.** | **Team leaders and trainers.** | **April 2014** | * **Team leaders** * **Trainers** * **Tax justice Africa** | **Development of campaign materials** |
| **Shop stewards and branch officials training** | **Joint training** | **Trainers.** | **May-October 2014** | * **Shopsteward** * **Branch officials** | * **Awareness by shop stewards and rank and file staff.** * **May day parade and presentation of tax justice slogans.** |
| **Review of the events** | **Evaluation** | **Team leaders and Trainers with PSI sub-regional office.** | **November and December 2014** | * **Team leaders** * **Trainers** * **PSI sub regional office.** | **Identify weaknesses and areas to improve on.** |