ZAMBIA CONGRESS OF TRADE UNIONS

TAX JUSTICE CAMPAIGN

**Activity 1:** **Awareness creation**

Target groups: (a) Executive Board Members

(b) N.E.C members of National Unions

(c) Regional and Branch leaders

(d) FFTUZ

How: Through meetings and workshops

Whose Responsibility: ZCTU Secretariat

When: Beginning First Quarter of 2014.

OUTCOMES:

Informed leadership on matters to do with the campaign for Tax Justice.

**Activity 2:**  **Partnering with other Non-State Actors**

Target Group: CSOs dealing with Social Economic Issues.

How: Holding Consultative meetings

Whose Responsibility: Secretariat

When: Second Quarter of 2014

OUT COMES: Partnerships formed with at least four CSOs

**Activity 3:** **Research on existing taxation framework**

How: (i) Discussions with Zambia Revenue Authority

(ii) Discussions with E.A.Z

(iii) Literature Review

When: First and Second Quarters of 2014

Whose Responsibility: Director of Research, ZCTU.

OUT COMES: Research Report

**ACTIVITY 4**: **Engaging Ministry of Finance**

Target: Minister of Finance.

How: Holding consultative meetings

Whose Responsibility: Secretariat

When: Third Quarter of 2014

OUT COMES: 2015 National Budget inclusive of ZCTU's submissions on Tax Justice measures.